## Sheet1
S.No | Vertical | Task | Priority | Estimated date of Completion | Status
1 | Analysis | Derived loads from primary requirements for any components should be shown using free body diagrams and backup calculation and need to be defined if its limit or ultimate. | 1 | 2024-09-08 | Complete
2 |  | Stress should include step by step slides: 1. Stress Requirements, Loads, critical loads, structural reduction, Free body diagrams, 2. list of components, Material properties of individual materials (including knock down factors), sizing, analysis etc. | 5 | 14/08/24 | Complete
3 |  | Refer to standard references which are shared, for formula’s used in calculations. | 2 | 2024-09-08 | Processing
4 |  | Assumptions for analysis need to be specified clearly. For example: Component is idealized as cantilever beam, assuming rigid connection with wing interface etc.. | 3 | 2024-12-08 | Processing
5 |  | Materials properties for each part & Weight estimation. | 4 | 2024-12-08 | Incomplete
|  | Install fucking solidworks | 0 | 2024-03-08 | Complete
6 | Design | Define how hardpoint is being fitted onto the UAV | 1 | 2024-09-08 | Complete
7 |  | Can work on aerodynamic design for drag reduction and show by simple hand calculations whether drag is within the requirement from compliance matrix. | 2 | 2024-09-08 | Complete
8 |  | Add the active negative displacement plungers | 3 | 2024-09-08 | Complete
9 |  | Check for Hardware impeding with rail guides | 4 | 2024-12-08 | Complete
10 |  | Details of how the Fail-safe redundancy is designed and implemented | 5 | 2024-12-08 | Complete
11 |  | Weight aPeeperrrrrsroximation | 6 | 2024-12-08 | Incomplete
12 |  | Latch mechanism in CAD showing with some exemplary Payload get latched to understand its merits and demerits. | 7 | 2024-12-08 | Incomplete
13 |  | GD&T, Tolerance Stackups | 8 | 14/08/24 | Processing
14 |  | Drawings can be improved covering all the feature details properly | 9 | 14/08/24 | Processing
15 |  | Latching mechanism shall be shown adding with Latch schematic and its functional description. | 10 | 14/08/24 | Incomplete
16 |  | Rail Mechanism integrating with the main UAV body with parts labelling. | 11 | 14/08/24 | Incomplete
17 |  | Describe production flow | 12 | 14/08/24 | Processing
18 |  | Assembly instructions should be provided with illustrations | 13 | 14/08/24 | Processing
19 | Design Analysis | Need to show case how redundant systems are carrying loads and choice of strength allowable for these. | 2 | 2024-09-08 | Incomplete
20 |  | Sizing/analysis should be shown for individual components using the concept of structural reduction. Always use coordinate system (x,y,z) in picture. | 1 | 2024-09-08 | Incomplete
21 | Presentation | Presentation slides need to be more clear from visual perspective, Use more pictorial representation (FBDs, Shear force, bending moment diagrams etc..) |  | 2024-09-08 | Incomplete
22 |  | Pictorial details explaining Working Principle of Under wing Pay load Hardpoint |  | 2024-12-08 | Incomplete
23 |  | Also, simulation of mechanism shall be worked out if possible or step wise showing unlatched and latched system. |  | 2024-12-08 | Incomplete
24 |  | Animation + combine with actual footage |  | 14/08/24 | Incomplete
25 | Requirements | The parent-child relationship from Tier-1 to Tier-3 should be shown. |  | 14/08/24 | Incomplete
26 |  | FMEA study has to be performed at this stage to understand the implication of failure of the hardpoint mechanism |  | 2024-09-08 | Complete
27 |  | Functional Hazard assessment at airplane level should be performed |  | 2024-09-08 | Processing
28 |  | Details on how the actuator specification was derived should have been provided. |  | 14/08/24 | Complete
29 |  | The MoC for all attributes affecting performance and affects the safety and integrity of the aircraft should have testing as the Method of Compliance. |  | 14/08/24 | Complete
30 |  | 3g and -3g directions should be specified in compliance matrix. For example 3g forward, aft, down up, lateral etc. |  | 2024-12-08 | Complete
31 |  | Need to define if 3g loads are limit or ultimate. |  | 2024-12-08 | Complete
32 |  | Emergency loads should be added in compliance matrix. |  |  | Complete
33 |  | Details on how the actuator specification is arrived shall be shown all with its technical details. |  | 2024-12-08 | Incomplete
34 |  | Proximity sensor specification details and its functional description |  | 2024-12-08 | Complete
35 |  | Architecture details of how the interface haPeeperrrrrsens between pilot’s command and the latching mechanism |  | 14/08/24 | Incomplete
36 |  | Block volume is to be T1 requirement, not T2 |  | 14/08/24 | Complete
37 |  | Release of payloads at various angles/attitudes needs to be added as requirement |  | 2024-12-08 | Incomplete
38 |  | Certifying authorities: CEMILAC, better documentation |  | 2024-09-08 | Processing
39 | Requirements Analysis | Natural frequency requirement should be added in compliance matrix as weight of hard point design can influence wing natural frequency largely. |  | 2024-09-08 | Incomplete
40 | Requirements Design Analysis | Take at least 2 requirements and explain the full process. a. Requirements flow down, FHA, FMEA b. Design and Analysis c. Verification compliance to these requirements. |  | 2024-12-08 | Incomplete
41 | Verification | Review all verification methods |  | 2024-12-08 | Incomplete
42 |  | Define all the tests to be done to carry out verification |  | 2024-12-08 | Incomplete

## Analysis
- +3g and -3g directions should be specified in compliance matrix. For example: 3g forward, aft, down up, lateral etc.
- Need to define if 3g loads are limit or ultimate.
- Derived loads from primary requirements for any components should be shown using free body diagrams and backup calculation and need to be defined if its limit of ultimate.
- Emergency loads should be added in compliance matrix.
- Natural frequency requirement should be added in compliance matrix as weight of hard point design can influence wing natural frequency largely.
- Need to show case how redundant systems are carrying loads and choice of strength allowable for these.
- Can work on aerodynamic design for drag reduction and show by simple hand calculations whether drag is within the requirement from compliance matrix.
- Stress should include step by step slides:
Stress Requirements, Loads, critical loads, structural reduction, Free body diagrams,
list of components, Material properties of individual materials (including knock down factors), sizing, analysis etc.
- Refer to standard references which are shared, for formula’s used in calculations.
- Assumptions for analysis need to be specified clearly. For example: Component is idealized as cantilever beam, assuming rigid connection with wing interface etc..
- Sizing/analysis should be shown for individual components using the concept of structural reduction. Always use coordinate system (x,y,z) in picture.